## Sheet1
Issues Description | Outcome | Chance of Risk | Impact of Outcome | Current Measures | Proposed Measures | Response measures | Date
Databases are hacked -possible loss of personal information | If this occurs, all data is possibly lost including databases of info and user 'Favourite lists'. Also possible that data could be stolen. | Low | Medium | Ensuring use and access from a scure location. Not leaving anything open or running in the background that could be prone to attack. | None | Inform users there has been a breach and to be careful of dubious emails. Request they change passwords immeadiately. | 2021-07-07
Device HDD fails/malfunctions - loss of all data | Data is lost, including all user information and 'Favourite lists' | Low | Low | Hold back up copies on other device or USB drives. | Possibly create a local server that mirrors the current 'in-use' HDD | Use back-up copies to restore lost information. If any excess/new data lost, inform users they will have to sadly re-input data again. | 2021-07-08
VM server goes down | Could result in program/website being down for an unspecified time, creating inconvenience for users | Low | Medium | None | Possibly migrate data to another VM server, whilst troubleshooting current one | Migrate to another VM. If not possible inform users of possible delay. | 2021-07-11
Accidental breach of data | Could result in user information being lost i.e. passwords, email, website info, etc. | Low | Medium | Ensure use of data and information is secured on a safe device and in a safe location. Additionally close any unecessary VM's or apps. | None | Inform users, data has been breached or possibly lost. Urge them to check for data loss and change passwords. | 2021-07-13
SQL Attack - potential MitM | Could result in certain info being acquired, again details such as passwords, emails, usernames, etc. | Low | Severe | Ensure network being used is secure | None | Inform users of the data breach and request they change passwords immeadiately. Urge them to be careful of any emails. | 2021-07-15